## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Account registration | Account registration | Guest | Register an account for customers who do not have an account to log in to the shop | Trúc Mai | Done | iter1 | iter2
2 | Log in | Log in | Content creator, Seller, Admin, Shipper, Customer | Users log in to the store through the Login Button on the Home page. As a Guest, he/she will click on the login button to go to the login page or it will automatically ask him/her to log in when he/she clicks to use the services. | Trúc Mai | Done | iter1 | iter 2
3 | Log out | Log out | Content creator, Seller, Admin, Shipper, Customer | User click on the logout button icon on the home page, system will automatically logout and go to the login page | Trúc Mai | Done | iter1 | iter 2
4 | Change password | Change password | Content creator, Seller, Admin, Shipper, Customer | User wants to change password for their account | Trúc Mai | Done | iter1 | iter 2
5 | Forgot password | Forgot password | Content creator, Seller, Admin, Shipper, Customer | User forget his/her password and wants to recover his/her password | Ngọc Tâm | Done | iter1 | iter 2
6 | View products | View products | Customer, Guest | The user wants to see the product list | Văn Tâm | Done | iter1 | iter 2
7 | Search products | Search products | Customer, Guest | Users who want to search for a certain product will click on the icon button on the Home page, a page will appear for the user to enter the product they want to search for. | Văn Tâm | Done | iter1 | iter 2
8 | Read contents | Read contents | Customer, Guest | User wants to read post details | Ngọc Thành | Done | iter2 | iter 3
9 | View personal information | View personal information | Customer | User wants to see personal information | Ngọc Tâm | Done | iter2 | iter 3
10 | Update personal information | Update personal information | Customer | Users want to change and update account information on the shop | Ngọc Tâm | Done | iter2 | iter 3
11 | Purchase | Purchase | Customer | Users want to purchase the item in the cart | Ngọc Tâm | Done | iter2 | iter 3
12 | Choose payment method | Choose payment method | Customer | Customer who wants to choose payment method | Ngọc Tâm | Done | iter2 | iter 3
13 | CRUD items in cart | CRUD items in cart | Customer | Customer wants to add the item to cart Customer want to delete item to cart Customer wants to update(update size, quantity) of the item in cart | Trúc Mai | Done | iter2 | iter 3
14 | View purchase history | View purchase history | Customer | User wants to view purchase history including products name, quantity, total price, and time order | Ngọc Tâm | Done | iter2 | iter 3
15 | Track Order | Track Order | Customer | After the process runs out, the goods will arrive at the delivery place | Ngọc Tâm | Done | iter3 | iter 4
16 | View contact information | View contact information | Customer, Guest | Users who want to see the shop's Contact Us will click the Contact Us button on the Home page, which will bring up a Contact Us page. | Anh Quân | Done | iter3 | iter 4
17 | Chat with the shop | Chat with the shop | Customer | User wants to chat with the store | Văn Tâm | Done | iter3 | iter 4
18 | CRUD content | CRUD content |  | Content creator can edit the posted content It provides an interface to create, retrieve, update, and delete content records in the system. | Ngọc Thành | Done | iter3 | iter 4
19 | Confirm order | Confirm order | Shipper | The shipper will confirm the order after receiving the goods and agree to deliver | Ngọc Thành | Done | iter4 | iter 5
20 | View order details | View order details | Shipper | Shipper wants to view order details, to to check delivered products | Văn Tâm | Done | iter4 | iter 5
21 | Confirm delivery | Confirm delivery | Shipper | Shipper set the status delivering in the case order in transit | Anh Quân | Done | iter4 | iter 5
22 | Check failed delivery | Check failed delivery | Shipper | Shipper wants to confirm delivery failed | Trúc Mai | Done | iter4 | iter 5
23 | CRUD products | CRUD products | Seller, Admin | The manager wants to CRUD the products in the store. It provides an interface to create, retrieve, update, and delete product records in the system. | Trúc Mai | Done | iter4 | iter 5
24 | View order status | View order status | Customer, Seller | Users want to see the status of their product orders in the shop, then click on the customer information icon button icon. Then will be transferred to the View Order Status page, the customer's product order status will be displayed and can be viewed by the user | Anh Quân | Done | iter4 | iter 5
25 | View sale history | View sale history | Seller, Admin | The user wants to see the history of the products sold in the store | Anh Quân | Done | iter5
26 | View the revenue | View the revenue | Seller, Admin | The user wants to view revenue of the products that have been sold in the store. Users can look up revenue history by looking up by date | Văn Tâm | Done | iter5
27 | View detailed order history | View detailed order history | Customer | The user wants to see the history of the products ordered in the store. Users can look up the history of orders placed by entering the order id and can look up by date | Anh Quân | Done | iter5
28 | CRUD employees | CRUD employees | Admin | The store administrator is the person who has the right to manage the overall sales website. Store administrator has the right to create, add, edit, and delete employees on the store's website. | Văn Tâm | Done | iter5

## Iter1
Iteration Tracking - Iteration 1
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Account registration | Account registration | Register an account for customers who do not have an account to log in to the shop | Trúc Mai | Done | II.1 | II.1
2 | Log in | Log in | Users log in to the store through the Login Button on the Home page. As a Guest, he/she will click on the login button to go to the login page or it will automatically ask him/her to log in when he/she clicks to use the services. | Trúc Mai | Done | II.2 | II.2
3 | Log out | Log out | User click on the logout button icon on the home page, system will automatically logout and go to the login page | Trúc Mai | Done | II.3 | II.3
4 | Change password | Change password | User wants to change password for their account | Trúc Mai | Done | II.4 | II.4
5 | Forgot password | Forgot password | User forget his/her password and wants to recover his/her password | Trúc Mai | Done | II.5 | II.5
6 | View products | View products | The user wants to see the product list | Văn Tâm | Done | II.6 | II.6
7 | Search products | Search products | Users who want to search for a certain product will click on the icon button on the Home page, a page will appear for the user to enter the product they want to search for. | Văn Tâm | Done | II.7 | II.7

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Read contents | Read contents | User wants to read post details | Ngọc Thành | Done | II.8 | III.8
2 | View personal information | View personal information | User wants to see personal information | Ngọc Tâm | Done | II.9 | III.9
3 | Update personal information | Update personal information | Users want to change and update account information on the shop | Ngọc Tâm | Done | II.10 | III.10
4 | Purchase | Purchase | Users want to purchase the item in the cart | Ngọc Tâm | Done | II.11 | III.11
5 | Choose payment method | Choose payment method | Customer who wants to choose payment method | Ngọc Tâm | Done | II.12 | III.12
6 | CRUD items in cart | CRUD items in cart | Customer wants to add the item to cart Customer want to delete item to cart Customer wants to update(update size, quantity) of the item in cart | Trúc Mai | Done | II.13 | III.13
7 | View purchase history | View purchase history | User wants to view purchase history including products name, quantity, total price, and time order | Ngọc Tâm | Done | II.14 | III.14

## Iter3
Iteration Tracking - Iteration 1
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Track Order | Track Order | After the process runs out, the goods will arrive at the delivery place | Ngọc Tâm | Done | II.15 | II.15
2 | View contact information | View contact information | Users who want to see the shop's Contact Us will click the Contact Us button on the Home page, which will bring up a Contact Us page. | Anh Quân | Done | II.16 | II.16
3 | Chat with the shop | Chat with the shop | User wants to chat with the store | Văn Tâm | Done | II.17 | II.17
4 | CRUD content | CRUD content | Content creator can edit the posted content It provides an interface to create, retrieve, update, and delete content records in the system. | Ngọc Thành | Done | II.18 | II.18

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Confirm order | Confirm order | The shipper will confirm the order after receiving the goods and agree to deliver | Ngọc Thành | Done | II.19 | II.19
2 | View order details | View order details | Shipper wants to view order details, to to check delivered products | Văn Tâm | Done | II.20 | II.20
3 | Confirm delivery | Confirm delivery | Shipper set the status delivering in the case order in transit | Anh Quân | Done | II.21 | II.21
4 | Check failed delivery | Check failed delivery | Shipper wants to confirm delivery failed | Trúc Mai | Done | II.22 | II.22
5 | CRUD products | CRUD products | The manager wants to CRUD the products in the store. It provides an interface to create, retrieve, update, and delete product records in the system. | Trúc Mai | Done | II.23 | II.23
6 | View order status | View order status | Users want to see the status of their product orders in the shop, then click on the customer information icon button icon. Then will be transferred to the View Order Status page, the customer's product order status will be displayed and can be viewed by the user | Anh Quân | Done | II.24 | II.24

## Iter5
Iteration Tracking - Iteration 5
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Confirm order | Confirm order | The shipper will confirm the order after receiving the goods and agree to deliver | Ngọc Thành | Done | II. 19 | II. 19
2 | View order details | View order details | Shipper wants to view order details, to to check delivered products | Văn Tâm | Done | II. 20 | II. 20
3 | Confirm delivery | Confirm delivery | Shipper set the status delivering in the case order in transit | Anh Quân | Done | II. 21 | II. 21
4 | Check failed delivery | Check failed delivery | Shipper wants to confirm delivery failed | Trúc Mai | Done | II. 22 | II. 22
5 | CRUD products | CRUD products | The manager wants to CRUD the products in the store | Trúc Mai | Done | II. 23 | II. 23
6 | View order status | View order status | Users want to see the status of their product orders in the shop, then click on the customer information icon button icon. Then will be transferred to the View Order Status page, the customer's product order status will be displayed and can be viewed by the user | Anh Quân | Done | II. 24 | II. 24
7 | View sale history | View sale history | The user wants to see the history of the products sold in the store | Anh Quân | Done | II. 25 | II. 25
8 | View the revenue | View the revenue | The user wants to view revenue of the products that have been sold in the store. Users can look up revenue history by looking up by date | Văn Tâm | Done | II. 26 | II. 26
9 | View detailed order history | View detailed order history | The user wants to see the history of the products ordered in the store. Users can look up the history of orders placed by entering the order id and can look up by date | Anh Quân | Done | II. 27 | II. 27
10 | CRUD employees | CRUD employees | The store administrator is the person who has the right to manage the overall sales website. Store administrator has the right to create, add, edit, and delete employees on the store's website. | Văn Tâm | Done | II. 28 | II. 28